## Backlog
ID | Story | Epic | SRS requirement | Assignee | Story points | Sprint | Acceptance criteria
BK-01 | Project scaffold: React (Vite) + Express + Mongoose, ESLint, .env.example, module folders | DevOps | NFR-005 | Bhuvan Raj H | 3 | 1 | App boots locally; folders follow SAD 4.1 (routes/controllers -> services -> repositories); no secrets committed
BK-02 | GitHub Actions CI: lint + tests on every PR | DevOps | NFR-005 | Bhuvan Raj H | 3 | 1 | Workflow runs on pull_request; failing lint/test blocks merge
BK-03 | Seed script: 1,000 books, 3 customers, 1 admin | DevOps | STP 6 | Anushka P | 3 | 1 | One command seeds the DB; books span Fiction, Non-fiction, Academic
BK-04 | Register API with unique email and bcrypt password hash | Auth & Security | FR-001, SEC-001 | Bhagath Naveen Mullakara | 5 | 1 | 201 on success; 409 EMAIL_EXISTS; stored hash is 60-char bcrypt; 8-char min password
BK-05 | Login API issuing JWT (role claim, 1 h expiry) | Auth & Security | FR-002 | Bhagath Naveen Mullakara | 3 | 1 | 200 with token/role/expiresIn; 401 generic message on bad credentials
BK-06 | Register / Login UI | Auth & Security | FR-001, FR-002 | Bhagath Naveen Mullakara | 3 | 1 | Customer can register, log in, log out; token kept in session storage
BK-07 | JWT verification middleware | Auth & Security | SEC-004 | Bhagath Naveen Mullakara | 3 | 1 | Missing/expired/tampered token returns 401 on protected routes
BK-08 | RBAC middleware for /admin routes | Auth & Security | SEC-002 | Bhagath Naveen Mullakara | 2 | 1 | Customer token gets 403 on every /admin endpoint
BK-09 | Sprint 1 demo video (1 min) uploaded to repo | Docs & Demo | Deliverable 2 | Bhagath Naveen Mullakara | 1 | 1 | Video shows working product; file committed to repo
BK-10 | Browse catalog API (public, paginated, limit <= 50) | Catalog & Search | FR-003 | Anushka P | 3 | 1 | GET /books works without login; limit 51 rejected or capped
BK-11 | Search by title, author or category | Catalog & Search | FR-004 | Anushka P | 5 | 1 | Matching books only; no-match returns empty list; injection payloads treated as text
BK-12 | Book detail API and page | Catalog & Search | FR-005 | Anushka P | 3 | 1 | Shows title, author, category, price, stock status, description, cover; 404 for unknown/disabled
BK-13 | Catalog UI: home, search results, book cards, out-of-stock label | Catalog & Search | FR-003, FR-005 | Anushka P | 5 | 1 | Responsive; Add to cart disabled when stock = 0
BK-14 | Add in-stock book to cart (login required) | Cart & Checkout | FR-006 | B S Keertana | 3 | 1 | Out-of-stock gives 409; unauthenticated gives 401
BK-15 | Update quantity / remove cart item | Cart & Checkout | FR-007 | B S Keertana | 2 | 1 | Qty 0/-1 gives 422; qty above stock gives 409
BK-16 | Cart total calculation (price x quantity) | Cart & Checkout | FR-008 | B S Keertana | 2 | 1 | Example 2x499.00 + 1x250.50 = 1248.50; empty cart = 0.00
BK-17 | Cart UI | Cart & Checkout | FR-006, FR-007, FR-008 | B S Keertana | 3 | 1 | Edit qty, remove items, see total
BK-18 | Payment adapter + mock payment service (SUCCESS / DECLINED / TIMEOUT) | Cart & Checkout | FR-016, NFR-006 | B S Keertana | 3 | 1 | Adapter interface stubbed in tests; no card data anywhere
BK-19 | Checkout API: validation, unique order number, stock reservation | Cart & Checkout | FR-009, FR-010 | B S Keertana | 5 | 1 | Empty cart/missing address rejected; address <= 300 chars; order number unique; decline creates no confirmed order
BK-20 | Admin: add / edit / disable books API | Admin | FR-013 | Bhuvan Raj H | 5 | 1 | Admin only; invalid data gives 422; disabled books hidden from customers
BK-21 | Admin: update stock quantity API | Admin | FR-014 | Bhuvan Raj H | 2 | 1 | Stock >= 0; negative gives 422
BK-22 | Admin catalog management UI | Admin | FR-013, FR-014 | Bhuvan Raj H | 5 | 1 | Add, edit, disable, stock update from dashboard
BK-23 | Input validation and sanitisation (express-validator, mongo-sanitize, length limits) | Auth & Security | SEC-003 | Bhagath Naveen Mullakara | 5 | 2 | Operator injection and script payloads neutralised; limits per SRS Appendix B
BK-24 | Central error envelope, helmet headers, request logging | Auth & Security | SEC-003, SEC-006 | Bhagath Naveen Mullakara | 3 | 2 | All errors use standard envelope; no stack traces to clients
BK-25 | Security event logging and login rate limit | Auth & Security | SEC-006 | Bhagath Naveen Mullakara | 3 | 2 | Failed login/unauthorised access logged; 11th login in 15 min gives 429
BK-26 | Verify no payment card data stored (schema/log review) | Auth & Security | SEC-005 | Bhagath Naveen Mullakara | 1 | 2 | Only paymentStatus and paymentRef persisted
BK-27 | Auth and security tests (TC-AUTH, TC-SEC) | Testing | SEC-001..006 | Bhagath Naveen Mullakara | 3 | 2 | Tests run in CI and pass
BK-28 | Update SRS/SAD/RTM for Auth module; document deviations | Docs & Demo | Deliverable 2 | Bhagath Naveen Mullakara | 2 | 2 | Deviations written down for final demo
BK-29 | Search performance: indexes + JMeter plan (50 users) | Catalog & Search | NFR-001 | Anushka P | 5 | 2 | p95 <= 1.5 s, error rate < 1%
BK-30 | Catalog tests (TC-CAT) | Testing | FR-003..005 | Anushka P | 3 | 2 | Tests run in CI and pass
BK-31 | Postman collection run in CI | Testing | SAD 3.7 | Anushka P | 3 | 2 | Collection covers main endpoints; Newman step in workflow
BK-32 | Health endpoint (/health) and uptime check | DevOps | NFR-002 | Anushka P | 2 | 2 | GET /health returns 200, 503 when DB is down; uptime log kept
BK-33 | Usability walkthrough: order in <= 5 screens | Testing | NFR-003 | Anushka P | 2 | 2 | Results recorded for test users
BK-34 | Update docs for Catalog module; document deviations | Docs & Demo | Deliverable 2 | Anushka P | 2 | 2 | Deviations written down for final demo
BK-35 | Sprint 2 demo video (2 min) uploaded to repo | Docs & Demo | Deliverable 2 | Anushka P | 1 | 2 | Working product; file committed to repo
BK-36 | Idempotency-Key on POST /orders (retry-safe) | Cart & Checkout | NFR-004 | B S Keertana | 5 | 2 | Retry after timeout yields exactly one order; replay returns 200
BK-37 | Order history and order detail (own orders only) | Cart & Checkout | FR-012 | B S Keertana | 3 | 2 | Other customer's order gives 404; empty history handled
BK-38 | Customer cancels own PLACED order (stock restored) | Cart & Checkout | SRS 6.5 | B S Keertana | 2 | 2 | Cancel after PROCESSING gives 409
BK-39 | Checkout, confirmation and order history UI | Cart & Checkout | FR-009, FR-012, NFR-003 | B S Keertana | 5 | 2 | Basic purchase within 5 primary screens
BK-40 | Cart and order tests (TC-CART, TC-ORD, TC-TRK, TC-TST) | Testing | FR-006..012, NFR-004 | B S Keertana | 3 | 2 | Tests run in CI and pass
BK-41 | Update docs for Cart & Checkout; document deviations | Docs & Demo | Deliverable 2 | B S Keertana | 2 | 2 | Deviations written down for final demo
BK-42 | Order status state machine (PLACED..CANCELLED) | Admin | FR-011 | Bhuvan Raj H | 3 | 2 | Invalid transition gives 409; statusHistory records actor/time
BK-43 | Admin order list and status update API | Admin | FR-015 | Bhuvan Raj H | 5 | 2 | Filter by status; customer sees staff-set status
BK-44 | Admin order management UI | Admin | FR-015 | Bhuvan Raj H | 3 | 2 | Incoming orders and status update from dashboard
BK-45 | Dockerfile + docker-compose | DevOps | STP 6 | Bhuvan Raj H | 3 | 2 | App and DB start with one command
BK-46 | Static analysis and npm audit in CI | DevOps | SAD 3.9 | Bhagath Naveen Mullakara | 2 | 2 | Scan step in workflow
BK-47 | Admin tests (TC-ADM) and development freeze | Testing | FR-013..015 | Bhuvan Raj H | 3 | 2 | Tests pass; main frozen at end of Sprint 2
BK-48 | Update docs for Admin module; document deviations | Docs & Demo | Deliverable 2 | Bhuvan Raj H | 2 | 2 | Deviations written down for final demo

## Summary
Story points per person per sprint
Assignee | Sprint 1 | Sprint 2 | Total
Anushka P | 19 | 18 | 37
B S Keertana | 18 | 20 | 38
Bhagath Naveen Mullakara | 17 | 19 | 36
Bhuvan Raj H | 18 | 19 | 37
Team total | 72 | 76 | 148
Stories per sprint
Sprint 1 | 22
Sprint 2 | 26
Requirements coverage check: FR-001..FR-016, NFR-001..006 and SEC-001..006 each appear in the Backlog 'SRS requirement' column.
Assumption: story points use a 1-2-3-5 scale (blue cells in Backlog are editable); sprint capacity target is about 17-20 points per person. Estimates are the team's to confirm.